## Sheet1
| Outstanding Issues in WIMs | Status | Test Required | Action required
1 | Modify the Admin and Support tools to be able to correct wrong axles, sloc input after packing and loading has been done |  |  | Change note required.
2 | Block truck from taking Weigh1 when Sales Order is deleted/archived in SAP |  |  | Change note required.
3 | Include a validation in WB screen which blocks truck from taking Weigh1 when Order allocated tonnage + tare weight exceeds allowable maximum tonnage + axle tolerance | In progress
4 | Build validation of the Rail packing process | In progress |  | Whole rail process needs to be revisited, it is not operating very smoothly. An alternative procedure need to be looked at in dealing with the rail.
5 | Modify the CSC screen for Transfer process to show Transporter against the STO input (when you enter STO) |  |  | Change note required.
6 | Include more details in the WB Customise Field Details eg. No. of Axles, Sloc, etc |  |  | Change note required.
7 | Rejection slip - rejection reason is misaligned - needs to be corrected / formatted better | Awaiting Assistance |  | New template required, please send a sample of the rejection slip not aligning correctly.
8 | Rejection transaction is causing duplication on bags report - this is urgent and needs to be resolved ASAP. Rejection more than 3 times causes havoc in the system | Completed for testing | Please test rejection and complete the order weigh out etc. Please test this with one weigh in and weigh out, as well as a few rejection with separate orders for each order type. | This needs investigation to determine why this is occuring.
9 | Create a screen to ease receipting of transferred product manually matching the STO, gatepass and GIS or Dnote for ZIC | In progress |  | New process being investigated.
10 | WB ticket - the Nett weight is misaligned and enhance the general format of the ticket | Awaiting Assistance |  | Please provide a sample so I can create a new template.
11 | The customised field for complete trucks has missing data eg. WB used etc | Awaiting Assistance |  | Please provide an example that can be reviewed, send screenshots so it can be ssen.
12 | Generate a screen for packing and loading for handhelds - to have 2 screen versions ie for PC and handhelds. The handheld screen to have date and time closed. | Available in PROD under application 5 and version 6. |  | Change will be made and made available in QAS for testing.
13 | Release of rotating trucks using CSC screen - this is oustanding | Completed for testing | Please test the release of the truck in the queue management system, please do a test directly after it has been weighed for the first time and also test after the truck has performed a few return trips. | Please test and provide feedback.
14 | Packing and Loading screen - amalgamate with Retail packinga and loading | Completed for testing | Please test for normal order types and also test for RSO types. | Please test and provide feedback.
15 | Removal of decimal points on weigh1, weigh2 and nett weight - WB screen | Completed for testing | Please confirm that the decimal has been removed while performing the other weigh in tests during the tests of different order types. | Needs to be investigated.
16 | After inspection, the truck reg disappears from screen. However when packing, loading, order or gatepass is assigned, the truck does not disappear from screen | I do not fully grasp the situation, please provide a more detailed examples/s. |  | Changes will be made in QAS for testing
17 | When packing, the shift of previous transaction remains on the screen - this needs to be re-inputted in every transaction and included in validation | Completed for testing | Please confirm that this is not automatically populating. | This will be changed, however this will lead to a change note if this is to be reversed.
18 | Bags tolerance to have 4 decimal places to allow eg 0.0035 | Completed for testing | Please test this and let me know. I have increased the field width to 7. This will allow 5 decimal position after the decimal point. | Please test this in qas and provide feedback. It might be possible already.
19 | Modify the loading screen to eliminate the ConsQ and Packing line input as it can't change from Packing screen |  |  | Change note required.